## Team Members & Roles
Team Members | Roles | Responsibilities
Zehra Buse Tüfekçi | Project Manager | Project planning and scheduling
| Backend Developer | Requirement analysis
| Frontend Developer | System design
| ML Developer | Dataset preprocessing
| Documentation Specialist | Model development and evaluation
| Tester / QA | Backend and Frontend implementation
Deployment management
Technical documentation preparation
Note : | All roles are performed by a single team member as part of an individual academic project.

## Project Proposal
Project Title
Ride Cancellation Prediction System Using Machine Learning
Project Overview
This project aims to develop a machine learning–based prediction model to estimate the likelihood of ride cancellations in ride-hailing platforms. The system will analyze historical ride data and identify patterns associated with cancellation behavior. The primary focus of this project is predictive modeling and analytical evaluation rather than building a fully production-ready commercial system. The developed model will be deployed using Hugging Face Spaces to demonstrate its functionality in a cloud-based environment. The project includes data preprocessing, exploratory data analysis (EDA), feature engineering, model training, evaluation, and basic deployment. The objective is to provide a decision-support tool that can assist platforms in understanding and reducing ride cancellations.
Problem Statement
Ride cancellations present a significant operational challenge for ride-hailing platforms, resulting in revenue loss, inefficient driver utilization, and reduced customer satisfaction. Cancellations may occur due to factors such as long waiting times, pricing issues, driver behavior, or user-related conditions. This project develops a machine learning–based demo prediction model to estimate the likelihood of ride cancellations using historical ride data. The model is designed as a prototype-level solution to demonstrate predictive feasibility and analytical evaluation rather than a production-ready system.
Project Objectives
To develop a machine learning–based demo model for predicting ride cancellations.
To identify key factors influencing ride cancellation behavior.
To evaluate and compare different machine learning models using standard performance metrics.
To deploy the model as a prototype on Hugging Face Spaces for demonstration purposes.
Target Users
Operations Teams :To explore how predictive insights can support operational decision-making related to ride cancellations.
Data Analysts & Data Scientists : To analyze cancellation patterns, evaluate model performance, and interpret feature importance.
Business & Decision Makers : To assess the potential business value of ride cancellation prediction using a demo-level model.
Academic Evaluators / Portfolio Reviewers: To evaluate the project as a demonstration of applied machine learning and data analytics skills.
Main Features (Demo System)
Ride cancellation probability prediction for individual rides
Feature importance visualization to explain model behavior
Model performance evaluation metrics (accuracy, precision, recall, F1-score)
Interactive demo interface for testing different input scenarios
Cloud-based prototype deployment on Hugging Face Spaces
Project Scope
In Scope
Data cleaning and preprocessing
Exploratory data analysis
Feature engineering
Machine learning model development
Model evaluation and performance analysis
Deployment on Hugging Face Spaces (demo-level)
Out of Scope
Real-time production system integration
Mobile or full-scale web application development
Large-scale distributed system architecture
Payment system integration
Live API connection to real ride-hailing platforms

## Project Timeline
Project Timeline (Weekly Plan)
Week | Phase | Key Activities | Deliverables
Week 1 | Problem Definition and Business Understanding | Define business problem and impact, identify stakeholders, define success metrics, understand dataset structure | Problem statement, business value explanation, project scope document
Week 2 | Data Exploration & Understanding | Load and inspect dataset, handle missing values, perform EDA, analyze cancellation patterns | Cleaned dataset, EDA visualizations, initial insights report
Week 3 | Feature Engineering & Data Preprocessing | Encode categorical variables, scale numerical features, create new features, train-test split | Final feature set, preprocessing pipeline, train-test datasets
Week 4 | Model Development | Train baseline model, train advanced models, hyperparameter tuning, model comparison | Trained models, model comparison table, selected best model
Week 5 | Model Evaluation & Interpretation | Evaluate models using metrics, confusion matrix analysis, feature importance, business impact analysis | Model evaluation report, feature importance analysis, business interpretation
Week 6 | Deployment | Deploy model, test deployed system, validate outputs | Deployed model
Week 7 | Final Documentation & Portfolio | Prepare final report, write technical & business documentation, prepare GitHub repository | Final project report, GitHub portfolio project

## Budget Planning
Budget Planning (Week-Based Distribution)
Week | Phase | Estimated Hours
Week 1 | Problem Definition & Business Understanding | 6
Week 2 | Data Exploration & Understanding | 12
Week 3 | Feature Engineering & Data Preprocessing | 10
Week 4 | Model Development | 15
Week 5 | Model Evaluation & Interpretation | 9
Week 6 | Deployment | 4
Week 7 | Final Documentation & Portfolio | 4
Total |  | 60
Budget Planning (Role-Based Time Allocation)
Role | Related Weeks | Total Hours
Project Manager | Week 1, 5 | 8
Backend Developer | Week 2–4 | 12
Frontend Developer | Week 4–5 | 8
ML Developer | Week 3–5 | 20
Documentation Specialist | Week 6–7 | 6
Tester / QA | Week 6–7 | 6
Total |  | 60
Budget Planning (Technical Resources)
Resource | Cost | Description
Python | Free | Core programming language
Pandas, NumPy, Scikit-learn | Free | Data processing and machine learning
Matplotlib / Seaborn | Free | Data visualization
Hugging Face | Free | Model deployment
Google Colab / Local Machine | Free | Development environment
GitHub | Free | Version control and portfolio
Total | 0 TL
Time-Based Budget (Opportunity Cost – Week Aligned)
Item | Hours | Related Weeks
Learning & Research | 15 | Week 1-3
Implementation | 35 | Week 3-6
Documentation | 10 | Week 6-7
Total | 60 Hours
Expected Business Value
Reduction in ride cancellations
Improved driver assignment strategies
Increased customer satisfaction
Lower operational costs
Data-driven decision making
Final Outputs
Machine learning prediction model
Business-focused analytical insights
Deployable demo system
Portfolio-ready project